# [Project name] Beneficiary Assessment Process Overview

This document outlines the anticipated activities associated with the [Project Name] Beneficiary Assessment beginning [Date X]. The main tasks associated with the different BA steps, along with relevant milestones and primary responsibilities, are included in the following table.

## Table 1: Overview of the Beneficary Assessment process for [Project name], [Year X]

| # | Steps | Date/ Period | Participants | Responsible |
| --- | --- | --- | --- | --- |
|  | Preliminary definition of assessment scope, tools and formats: - BA Inception Report (including methodological approach, overview of research areas and selection criteria) - Modality of assessment (finalizing process map and key roles) | Months 1-2 | Trainer/Backstopper, funder representative, implementing partner representative, National Facilitator | Trainer/Backstopper and National Facilitator |
|  | Definition of the roles of participating actors - Overview of participating actors - Selection criteria and role of actors | Month 1 | Trainer/Backstopper, funder representative, implementing partner representative, National Facilitator | National Facilitator |
|  | Establishment of TORs and contracts - Facilitators - Co-Facilitators - Citizen Observers | Month 2 | Funder to provide comments | Trainer/Backstopper for ToRs, funder for contracts |
|  | Selection of areas/actors to be assessed - Selection of co-facilitator(s) - Selection of research locations - Preparation of implementing partners for CO and household (HH) selection - Selection of participating families to be assessed, preparation of background info - Selection of citizen observers (COs) | Month 3 | National Facilitator to work with implementing partner team to identify appropriate areas and approach to CO selection (latter done by appropriate local actors - TBD) | National Facilitator |
|  | Training of/co-planning with facilitators - Organise training of facilitators (invitation, logistics etc.) - Preparation of training curriculum - Creation of guidelines for interviews (Household and Focus Group levels) - Training of facilitators | Month 4 (1 week) | National Facilitator and Co-facilitator, Trainer/Backstopper | Trainer/Backstopper in consultation with funder and facilitator |
|  | Presentation of process to relevant actors, training of COs - Organise training of COs (invitation, logistics etc.) - Preparation of information and training curriculum - Training of COs (including finalization of Assessment framework: questions for semi-structured interviews, formats) - Planning for implementation | Month 4 (1 week) | Trainer/backstopper to conduct training, project implementer to coordinate logistics Planning in parallel with CO training | National Facilitator supported by Trainer/Backstopper |
|  | Field testing & adjustments - Conduct field testing in a community (not being part of assessment!) - Analyse findings of field testing - Make necessary adjustments for implementation (formats, interview modality, data collection etc.) - Fine-tune planning and get shared understanding for the implementation | Month 4 (2 days) | Trainer/Backstopper to support field testing and adaptation, project implementer to coordinate logistics | National Facilitator |
|  | Implementation - Travel to first assessment sites - Recall and agree with community on programme of assessment (2 days) - 1st day: assessment at household level (interviews), consolidation - 2nd day: Focus group meetings for community level perspective followed by feedback of results to community - Travel to next assessment sites, etc. | Month 5 (2 weeks) | Focus groups to include women and men representative of key social/institutional groups. Project implementer to support with logistics (NOTE: No project vehicles or staff to be used during field research phase!) | National Facilitator, COs |
|  | Data processing and analysis - Consolidate information, data input, quality control - Data analysis according to established procedure - Presentation of results according to established formats - Prepare presentation of validation workshop | Month 6 (2 weeks) | Trainer/Backstopper to support. Project implementer to coordinate logistics, invitations for validation workshop | National Facilitator |
|  | Validation workshop - Preparation of workshop (programme, logistics) - Presentation of results and discussion - Reach consensus (?) on required changes - Feedback of participants on methodology | Month 6 (1.5 days) | - COs - Project partners - Project implementer - Funder - Others as feasible | National Facilitator and Trainer/Backstopper |
|  | Meeting for final analysis and interpretation of results - Final analysis of the results incl. findings of validation workshop - Define needs for adjustments and further cross-checks. - Define structure for final report - Revise methodology - Agree on collaboration and time plan for concluding the analysis and draft report | Month 7 | Trainer/Backstopper to support | National Facilitator |
|  | Final report - Completion of draft report - Elaboration of final draft report for submission to funder1 - Revision of report and feedback from funder - Elaboration of final report - Dissemination of report | Month 7 (2 weeks) | Facilitator, Trainer/Backstopper to support | 12.1-12.4 National Facilitator 12.5 Trainer/Backstopper, Funder |