## Table 1: Overview of the Beneficiary Assessment process for project X – SDC cooperation office XYZ, months1-4 20xx

| # | Steps | Date/ Period | Participants | Responsible |
| --- | --- | --- | --- | --- |
|  | Preliminary definition of assessment scope, tools and formats: - BA Inception mission and report (including methodological approach, overview of research areas and selection criteria) - Modality of assessment (finalizing process map and key roles) | 14th – 19th month1 | Trainer/Backstopper, National Facilitator, SDC and implementing partner representative | Trainer/Backstopper and National Facilitator |
|  | Definition of the roles, selection of Peer Observers (POs) and participating actors - Overview of participating actors - Selection criteria and role of actors | 20th – 24th month 1 | National Facilitator, implementing partner representatives | National Facilitator |
|  | Selection of areas/actors to be assessed - Selection of research locations and cohorts - Preparation of implementing partners/ providers - Selection of participating groups to be assessed and types of enterprises - Selection of Peer Observers (POs) | 28th month1– 6th month2 | National Facilitator to work with providers /implementing partners team to identify appropriate areas and approach for selection POs | National Facilitator |
|  | Presentation of process to relevant actors, methodology refinement, training of Peer Observers (Pos) - Organise training of POs (invitation, logistics etc.) - Methodology refinement workshop (Incl. preparation of information and training curriculum) - Training of POs (including finalization of Assessment framework: questions for semi-structured interviews, formats) - Planning for implementation | 9th – 17th month2 Methodology refinement workshop: 13-14 month2 PO Training: 15-17 month2 | Trainer/Backstopper, National Facilitator and Co-facilitator to conduct training, project implementer to support logistics coordination Planning with POs | National Facilitator, Co-facilitator supported by Trainer/Backstopper |
|  | Field testing& adjustments - Conduct field testing in a community (not being part of assessment!) - Analyse findings of field testing - Make necessary adjustments for implementation (formats, interview modality, data collection etc) - Fine-tune planning and get shared understanding for the implementation | 18th – 19th month2 (2days) | National facilitator; Trainer/Backstopper to support field testing and adaptation, project implementer to coordinate logistics | National Facilitator |
|  | Implementation - Two teams travel in parallel to assessment in 2 regions (1 team responsible for 1 region) - Recall and agree with providers on programme of assessment (1 day) - 1st day: assessment at enterprises (interviews), consolidation - 2nd day: Focus group discussions for groups perspective - 3rd day: Share highlights on preliminary findings with providers and travel to next assessment sites (districts), etc | 23rd month2 – 3rd month3 (12 days, including POs travel days i.e. from & back home) | Focus groups to include Girls and Boys in different cohorts and enterprises. Local project partners to support with contacts of groups or enterprises | National Facilitator, Co-facilitator and POs |
|  | Data processing and analysis - Consolidate information, data input, quality control - Data analysis according to established procedure - Presentation of results according to established formats - Prepare presentation of validation workshop | 4th – 6th month3 (3 days) | Trainer/Backstopper to support. Project implementer to coordinate logistics, invitations for validation workshop | National Facilitator and Trainer/Backstopper |
|  | Validation workshop - Preparation of workshop (programme, logistics) - Presentation of results and discussion - Incorporate required changes - Feedback of participants on methodology | 8th – 9th month3 (1.5 days) | - POs - Project partners - District Focal Persons - Project implementer - Funder - Others as feasible | National Facilitator and Trainer/Backstopper |
|  | Further analysis and interpretation of results - Final analysis of the results incl. findings of validation workshop - Define needs for adjustments and further cross-checks. - Define structure for final report - Prepare draft report and submission to SDC | 10th – 14th month3 | National Facilitator and Trainer/Backstopper to support | National Facilitator and Trainer/Backstopper |
|  | Submission of draft report | 17th month3 | Trainer/Backstopper | Trainer/Backstopper |
|  | Final report - Revision of report and feedback from SDC - Elaboration of final report - Dissemination of report | 18th month3 - 01 month4 | Trainer/Backstopper and National Facilitator | Trainer/Backstoppers |
|  | Learning event - Dissemination of key lessons - Knowledge sharing and replications | 2nd month4 | - Project partners - District Focal Persons - Project implementers/staff - Funders/donors - Others as feasible | National Facilitator supported by Trainer/Backstopper |